## Zeitplan
Projectplan |  |  | Project start |  |  | 2023-01-30
Customer: |  | EDSSI L2 - Task 2.5 - Student housing Web-Application
Status: |  | 2023-02-21
Pos. | Group | Task | Responsibility | Effort (h) | Start | Date/End | Calendar week
[7 empty] | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
 | time axis 2023-01-30 to 2025-05-26
0 | Milestones
|  | Framework set up |  |  |  | 2023-03-02
|  | Sign-On implemented |  |  |  | 2023-03-29
|  | Signature component integrated |  |  |  | 2023-04-27
|  | Housing part developed |  |  |  | 2023-06-15
|  | Testing completed |  |  |  | 2023-07-27
1 | Project start |  | SWKA | 5 | 2023-02-09 | 2023-02-16
2023-01-01 |  | Setup of a project management tool (Trello, Notion) | NQ | 3 | 2023-02-09 | 2023-02-16
2023-02-01 |  | Set-up Github-Repo | NQ | 1 | 2023-02-09 | 2023-02-16
2023-03-01 |  | Cloning of the existing repos (SSO, EduSign) | NQ | 1 | 2023-02-09 | 2023-02-16
2 | Infrastructure Set-Up |  | SWKA | 20 | 2023-02-09 | 2023-02-23
2023-01-02 |  | Server setup | NQ | 16 | 2023-02-09 | 2023-02-23
2023-02-02 |  | Test domain registration | NQ | 2 | 2023-02-09 | 2023-02-23
2023-03-02 |  | Registration of a mailing service | NQ | 2 | 2023-02-09 | 2023-02-23
3 | Framework/Front-End/Infrastructure |  | SWKA | 12 | 2023-02-16 | 2023-03-02
2023-01-03 |  | Selection of a framework (React, Angular) | NQ | 6 | 2023-02-16 | 2023-02-23
2023-02-03 |  | Selection of a graphical front end theme | NQ | 2 | 2023-02-23 | 2023-03-02
2023-03-03 |  | Selection/setup of the cloud infra | NQ | 4 | 2023-02-23 | 2023-03-02
2023-04-03 |  | Setting up the framework | NQ |  | 2023-02-23 | 2023-03-02
4 | Sign-On |  | SWKA | 124 | 2023-02-23 | 2023-03-30
2023-01-04 |  | Conclusion of contract DFN | NQ | 4 | 2023-02-23 | 2023-03-02
2023-02-04 |  | Integration of the existing single sign-on | NQ | 120 | 2023-03-02 | 2023-03-30
5 | Signature |  | SWKA | 120 | 2023-02-09 | 2023-04-27
2023-01-05 |  | Familiarization with "e-signature" project team | SWKA |  | 2023-02-09 | 2023-03-02
2023-02-05 |  | Integration of the signing component | NQ | 120 | 2023-03-30 | 2023-04-27
6 | Housing-Part |  | SWKA | 248 | 2023-04-27 | 2023-06-15
2023-01-06 |  | Development Profile Screen | NQ | 24 | 2023-04-27 | 2023-05-04
2023-02-06 |  | Development of a contract screen | NQ | 188 | 2023-05-04 | 2023-05-25
2023-03-06 |  | Planning booking screen | SWKA |  | 2023-05-04 | 2023-05-25
2023-04-06 |  | Development booking screen | NQ | 32 | 2023-05-25 | 2023-06-08
2023-05-06 |  | Planning error message screen | SWKA |  | 2023-05-25 | 2023-06-08
2023-06-06 |  | Development error message screen | NQ | 4 | 2023-06-08 | 2023-06-15
7 | Testing/Documentation |  | SWKA | 32 | 2023-04-27 | 2023-07-27
2023-01-07 |  | Automation Testing | NQ | 32 | 2023-04-27 | 2023-06-15
2023-02-07 |  | Testing with partners | SWKA |  | 2023-06-15 | 2023-07-13
2023-03-07 |  | Development notes in English (readme.md) | NQ |  | 2023-07-13 | 2023-07-27
2023-04-07 |  | Development documentation incl. screenshots in English | NQ |  | 2023-07-13 | 2023-07-27
Formulas:
Date/End = IF(MAX([Date/End, row below]:G17)=0,"",MAX([Date/End, row below]:G17))
Date/End = [Start]+28
Start = IF(MIN([Start, row below]:F17)=0,"",MIN([Start, row below]:F17))
Start = [Date/End, row above]

## Arbeitspakete
Arbeitspakete | To Dos | Akteure | Status | Informiert? | Notizen
Setup of a project management tool (Trello, Notion)
Set-up Github-Repo
Cloning of the existing repos (SSO, EduSign)
Server setup
Test domain registration
Registration of a mailing service
Selection of a framework (React, Angular)
Selection of a graphical front end theme
Selection/setup of the cloud infra
Setting up the framework
Conclusion of contract DFN
Integration of the existing single sign-on
Familiarization with "e-signature" project team
Integration of the signing component
Development Profile Screen
Development of a contract screen
Planning booking screen
Development booking screen
Planning error message screen
Development error message screen
Automation Testing
Testing with partners
Development notes in English (readme.md)
Development documentation incl. screenshots in English