## PM ceilings
| Partners | Person-month ceiling | Taken from EDSSI
1 | HUB | 5330
2 | EUF | 5601
3 | GEANT | 8500
4 | SRCE | 2800
5 | UB | 5000
6 | AUTh | 2500
7 | CNOUS | 6916
8 | DSW | 6688
9 | SRC | 10000
10 | ECSTA | 6000
11 | ELTE | 4000
12 | ENDISU | 10000
13 | NU | 5000
14 | EYCA | 6245

## Workload (person-month)
Activities (person-month) | A1 | [9 empty] | A2 | [9 empty] | A3 | [9 empty] | A4 | [9 empty] | A5 | [9 empty] | A6 | [9 empty] | A7
Tasks | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 1.6 | 1.7 | 1.8 | 1.9 | T | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 2.7 | 2.8 | 2.9 | T | 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 3.6 | 3.7 | 3.8 | 3.9 | T | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6 | 4.7 | 4.8 | 4.9/10 | T | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 5.6 | 5.7 | 5.8 | 5.9 | T | 6.1 | 6.2 | 6.3 | 6.4 | 6.5 | 6.6 | 6.7 | 6.8 | 6.9 | T | 7.1 | 7.2 | 7.3 | 7.4 | 7.5 | 7.6 | 7.7 | 7.8 | 7.9 | T | 1.9
HUB | A1 1.1: 8; A1 1.2: 18; A1 1.3: 0.5; A1 1.4: 1; A1 1.5: 4 | 31.5 | 0.5 | [8 empty] | 0.5 | 0.5 | 1 | 9 | 1 | [5 empty] | 11.5 | [7 empty] | 4 |  | 4 | 0.5 | [5 empty] | 0.5 |  |  | 1 | 13.5 | 1.5 |  | 1.5 | [5 empty] | 16.5 | [9 empty] | 0
EUF | A1 1.1: 0.5 | 0.5 | [5 empty] | 2 |  |  |  | 2 |  |  | 0 | 2 | [5 empty] | 2 |  | 3 |  |  |  |  | 0.5 |  | 12 | 15.5 | 6.5 | 1 | 3 | 1 | 2 | 4 | 1 |  |  | 18.5 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
GEANT | A1 1.1: 0.5; A1 1.3: 0.5 | 1 | 1.5 | 0.5 | [7 empty] | 2 |  |  | 3 | 1 | [5 empty] | 4 | 8 | 5 | 2 |  | 3 |  |  |  | 1 | 19 | 0.5 |  |  |  | 1 | 4 | 0.5 |  |  | 6 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
SRCE | A1 1.1: 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 | 1 |  | 10.5 | 1 | [5 empty] | 12.5 | [9 empty] | 0 | [9 empty] | 0 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
UB | A1 1.1: 0.5 | 0.5 | 0.5 | 0.5 | 6 | [6 empty] | 7 | 6 | 2 | 8.5 | [6 empty] | 16.5 | [9 empty] | 0 | [9 empty] | 0 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
AUTh | A1 1.1: 0.5 | 0.5 | 0.5 | 6 |  | 1 | [5 empty] | 7.5 |  | 1 | 11.5 | [6 empty] | 12.5 |  |  |  | 3 | [5 empty] | 3 | 0.5 |  | 1 |  |  |  | 0.5 |  |  | 2 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
CNOUS | A1 1.1: 0.5; A1 1.5: 0.5; A1 1.6: 0.5 | 1.5 | 0.5 |  |  |  | 1 |  |  |  |  | 1.5 |  |  | 1.5 | [6 empty] | 1.5 | [5 empty] | 3 |  |  |  | 3 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
STW | A1 1.1: 0.5; A1 1.5: 0.5 | 1 | 0.5 |  |  |  | 2 |  |  |  |  | 2.5 |  | 1 | 5.5 | [6 empty] | 6.5 | [9 empty] | 0 |  |  |  |  | 0.5 |  | 0.5 |  |  | 1 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
SRC | A1 1.3: 0.5 | 0.5 | 6.5 | 8.5 | [7 empty] | 15 | 0.5 | 1 | 0.5 | 1 | [5 empty] | 3 |  |  | 1 | [6 empty] | 1 | 0.5 | [5 empty] | 0.5 |  |  | 1 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
ECSTA | [9 empty] | 0 | [9 empty] | 0 |  |  | 0 | [6 empty] | 0 | [9 empty] | 0 |  |  |  | 2 | 0.5 | 7 |  |  |  | 9.5 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
ELTE | A1 1.1: 0.5 | 0.5 | 0.5 | [8 empty] | 0.5 |  |  | 8.5 | [6 empty] | 8.5 | [9 empty] | 0 | [9 empty] | 0 | 0.5 |  | 2 |  | 2 |  |  |  |  | 4.5 | [9 empty] | 0
ENDISU | A1 1.1: 0.5 | 0.5 | [9 empty] | 0 |  |  | 1.5 | [6 empty] | 1.5 | [9 empty] | 0 | [9 empty] | 0 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
NU | A1 1.1: 0.5; A1 1.4: 2; A1 1.6: 7 | 9.5 |  |  |  |  | 1 |  |  |  |  | 1 |  |  | 8.5 | [6 empty] | 8.5 | [9 empty] | 0 | [6 empty] | 0.5 |  |  | 0.5 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
EYCA | A1 1.1: 0.5; A1 1.4: 4 | 4.5 | [9 empty] | 0 |  |  | 0 | 1 | [5 empty] | 1 | [9 empty] | 0 | [9 empty] | 0 | 0.5 | [8 empty] | 0.5 | [9 empty] | 0
0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 0 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0
0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 0 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0
Total | 13.5 | 18 | 1.5 | 7 | 5 | 7.5 | 0 | 0 | 0 | 52.5 | 11.5 | 15.5 | 6 | 1 | 4 | 2 | 0 | 0 | 0 | 40 | 8 | 6 | 68.5 | 7 | 0 | 0 | 0 | 0 | 0 | 89.5 | 8 | 8 | 3 | 3 | 3 | 3 | 0.5 | 4 | 13 | 45.5 | 8.5 | 1 | 4 | 3 | 4.5 | 15 | 4 | 0 | 0 | 40 | 20 | 1.5 | 2 | 1.5 | 2 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtasks calculation of A3 | [15 empty] | 1 | 2 | 3 | 4 | 5 | T
HUB | [15 empty] | 8 | 1 |  |  |  | 9
EUF | [20 empty] | 0
GEANT | [18 empty] | 3 |  | 3
SRCE | [15 empty] | 10 | 0.5 |  |  |  | 10.5
UB | [15 empty] | 8 | 0.5 |  |  |  | 8.5
AUTh | [15 empty] | 8 | 0.5 |  | 3 |  | 11.5
CNOUS | [16 empty] | 0.5 | 1 |  |  | 1.5
STW | [16 empty] | 0.5 | 2 | 3 |  | 5.5
SRC | [18 empty] | 0.5 |  | 0.5
ECSTA | [20 empty] | 0
ELTE | [15 empty] | 8 | 0.5 |  |  |  | 8.5
ENDISU | [16 empty] | 0.5 | 1 |  |  | 1.5
NU | [15 empty] | 8 | 0.5 |  |  |  | 8.5
EYCA | [20 empty] | 0

## Final budget per activity
in EUR | Direct eligible costs |  |  |  |  | Indirect eligible costs | Total eligible costs | Estimated CEF contribution
| Personnel costs |  | Subcontracting costs | Other costs | Total
| Person-month | Total | [6 empty] | Max budget (in k)
Activity 1 | 52.5 | 289010 | 0 | 0 | 289010 | 20034.665 | 309044.665 | 309044.665 | 450
HU | 31.5 | 167895 |  |  | 167895 | 11752.65 | 179647.65 | 179647.65
EUF | 0.5 | 2800.5 |  |  | 2800.5 |  | 2800.5 | 2800.5
GEANT | 1 | 8500 |  |  | 8500 | 595 | 9095 | 9095
SRCE | 0.5 | 1400 |  |  | 1400 | 98 | 1498 | 1498
UB | 0.5 | 2500 |  |  | 2500 | 175 | 2675 | 2675
AUTh | 0.5 | 1250 |  |  | 1250 | 87.5 | 1337.5 | 1337.5
CNOUS | 1.5 | 10374 |  |  | 10374 | 726.18 | 11100.18 | 11100.18
DSW | 1 | 6688 |  |  | 6688 | 468.16 | 7156.16 | 7156.16
SRC | 0.5 | 5000 |  |  | 5000 | 350 | 5350 | 5350
ECSTA | 0 | 0 |  |  | 0 | 0 | 0 | 0
ELTE | 0.5 | 2000 |  |  | 2000 | 140 | 2140 | 2140
ENDISU | 0.5 | 5000 |  |  | 5000 | 350 | 5350 | 5350
NU | 9.5 | 47500 |  |  | 47500 | 3325 | 50825 | 50825
EYCA | 4.5 | 28102.5 |  |  | 28102.5 | 1967.175 | 30069.675 | 30069.675
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 2 | 40 | 217446 | 104515.1 | 0 | 324626.1 | 14437.08 | 339249.73 | 339249.73 | 450
HU | 0.5 | 2665 |  |  | 2665 | 186.55 | 2851.55 | 2851.55
EUF | 2 | 11202 |  |  | 11202 |  | 11202 | 11202
GEANT | 2 | 17000 |  |  | 17000 | 1190 | 18190 | 18190
SRCE | 0.5 | 1400 |  |  | 1400 | 98 | 1498 | 1498
UB | 7 | 35000 |  |  | 35000 | 2450 | 37450 | 37450
AUTh | 7.5 | 18750 | 3000 |  | 21750 | 1312.5 | 23062.5 | 23062.5
CNOUS | 1.5 | 10374 |  |  | 10374 | 726.18 | 11100.18 | 11100.18
STW | 2.5 | 16720 | 51515.1 |  | 68235.1 | 1170.4 | 69405.5 | 69405.5
SRC | 15 | 100000 | 50000 |  | 150000 | 7000 | 157000 | 157000
ECSTA | 0 | 0 |  |  | 0 | 0 | 0 | 0
ELTE | 0.5 | 2000 |  |  | 2000 | 140 | 2140 | 2140
ENDISU | 0 | 0 |  |  | 0 | 0 | 0 | 0
NU | 1 | 5000 |  |  | 5000 | 350 | 5350 | 5350
EYCA | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 3 | 89.5 | 436838 | 30000 | 2500 | 469338 | 29969.52 | 499307.52 | 499307.52 | 450
HU | 11.5 | 61295 |  |  | 61295 | 4290.65 | 65585.65 | 65585.65
EUF | 2 | 11202 |  |  | 11202 |  | 11202 | 11202
GEANT | 4 | 34000 |  |  | 34000 | 2380 | 36380 | 36380
SRCE | 12.5 | 35000 |  | 500 | 35500 | 2485 | 37985 | 37985
UB | 16.5 | 82500 |  | 500 | 83000 | 5810 | 88810 | 88810
AUTh | 12.5 | 31250 |  | 500 | 31750 | 2222.5 | 33972.5 | 33972.5
CNOUS | 1.5 | 10374 | 10000 |  | 20374 | 726.18 | 21100.18 | 21100.18
STW | 6.5 | 43472 | 10000 |  | 53472 | 3043.04 | 56515.04 | 56515.04
SRC | 3 | 30000 |  |  | 30000 | 2100 | 32100 | 32100
ECSTA | 0 | 0 |  |  | 0 | 0 | 0 | 0
ELTE | 8.5 | 34000 |  | 500 | 34500 | 2415 | 36915 | 36915
ENDISU | 1.5 | 15000 | 10000 |  | 25000 | 1050 | 26050 | 26050
NU | 8.5 | 42500 |  | 500 | 43000 | 3010 | 46010 | 46010
EYCA | 1 | 6245 |  |  | 6245 | 437.15 | 6682.15 | 6682.15
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 4 | 45.5 | 307883.5 | 18000 | 0 | 325883.5 | 15474.76 | 341358.26 | 341358.26 | 200
HU | 4 | 21320 |  |  | 21320 | 1492.4 | 22812.4 | 22812.4
EUF | 15.5 | 86815.5 |  |  | 86815.5 |  | 86815.5 | 86815.5
GEANT | 19 | 161500 | 18000 |  | 179500 | 11305 | 190805 | 190805
SRCE | 0 | 0 |  |  | 0 | 0 | 0 | 0
UB | 0 | 0 |  |  | 0 | 0 | 0 | 0
AUTh | 3 | 7500 |  |  | 7500 | 525 | 8025 | 8025
CNOUS | 3 | 20748 |  |  | 20748 | 1452.36 | 22200.36 | 22200.36
STW | 0 | 0 |  |  | 0 | 0 | 0 | 0
SRC | 1 | 10000 |  |  | 10000 | 700 | 10700 | 10700
ECSTA | 0 | 0 |  |  | 0 | 0 | 0 | 0
ELTE | 0 | 0 |  |  | 0 | 0 | 0 | 0
ENDISU | 0 | 0 |  |  | 0 | 0 | 0 | 0
NU | 0 | 0 |  |  | 0 | 0 | 0 | 0
EYCA | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 5 | 40 | 244594.5 | 0 | 32100 | 276694.5 | 11506.32 | 288200.82 | 288200.82 | 250
HU | 1 | 5330 |  |  | 5330 | 373.1 | 5703.1 | 5703.1
EUF | 18.5 | 103618.5 |  | 8700 | 112318.5 |  | 112318.5 | 112318.5
GEANT | 6 | 51000 |  | 2700 | 53700 | 3759 | 57459 | 57459
SRCE | 0 | 0 |  |  | 0 | 0 | 0 | 0
UB | 0 | 0 |  |  | 0 | 0 | 0 | 0
AUTh | 2 | 5000 |  |  | 5000 | 350 | 5350 | 5350
CNOUS | 0.5 | 3458 |  |  | 3458 | 242.06 | 3700.06 | 3700.06
STW | 1 | 6688 |  |  | 6688 | 468.16 | 7156.16 | 7156.16
SRC | 1 | 10000 |  |  | 10000 | 700 | 10700 | 10700
ECSTA | 9.5 | 57000 |  | 20700 | 77700 | 5439 | 83139 | 83139
ELTE | 0 | 0 |  |  | 0 | 0 | 0 | 0
ENDISU | 0 | 0 |  |  | 0 | 0 | 0 | 0
NU | 0.5 | 2500 |  |  | 2500 | 175 | 2675 | 2675
EYCA | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 6 | 27 | 143570 | 0 | 58800 | 202370 | 13675.865 | 216045.865 | 216045.865 | 200
HU | 16.5 | 87945 |  | 4200 | 92145 | 6450.15 | 98595.15 | 98595.15
EUF | 0.5 | 2800.5 |  | 4200 | 7000.5 | 0 | 7000.5 | 7000.5
GEANT | 0.5 | 4250 |  | 4200 | 8450 | 591.5 | 9041.5 | 9041.5
SRCE | 0.5 | 1400 |  | 4200 | 5600 | 392 | 5992 | 5992
UB | 0.5 | 2500 |  | 4200 | 6700 | 469 | 7169 | 7169
AUTh | 0.5 | 1250 |  | 4200 | 5450 | 381.5 | 5831.5 | 5831.5
CNOUS | 0.5 | 3458 |  | 4200 | 7658 | 536.06 | 8194.06 | 8194.06
STW | 0.5 | 3344 |  | 4200 | 7544 | 528.08 | 8072.08 | 8072.08
SRC | 0.5 | 5000 |  | 4200 | 9200 | 644 | 9844 | 9844
ECSTA | 0.5 | 3000 |  | 4200 | 7200 | 504 | 7704 | 7704
ELTE | 4.5 | 18000 |  | 4200 | 22200 | 1554 | 23754 | 23754
ENDISU | 0.5 | 5000 |  | 4200 | 9200 | 644 | 9844 | 9844
NU | 0.5 | 2500 |  | 4200 | 6700 | 469 | 7169 | 7169
EYCA | 0.5 | 3122.5 |  | 4200 | 7322.5 | 512.575 | 7835.075 | 7835.075
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Activity 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HU | 0 | 0 |  |  | 0 | 0 | 0 | 0
EUF | 0 | 0 |  |  | 0 |  | 0 | 0
GEANT | 0 | 0 |  |  | 0 | 0 | 0 | 0
SRCE | 0 | 0 |  |  | 0 | 0 | 0 | 0
UB | 0 | 0 |  |  | 0 | 0 | 0 | 0
AUTh | 0 | 0 |  |  | 0 | 0 | 0 | 0
CNOUS | 0 | 0 |  |  | 0 | 0 | 0 | 0
STW | 0 | 0 |  |  | 0 | 0 | 0 | 0
SRC | 0 | 0 |  |  | 0 | 0 | 0 | 0
ECSTA | 0 | 0 |  |  | 0 | 0 | 0 | 0
ELTE | 0 | 0 |  |  | 0 | 0 | 0 | 0
ENDISU | 0 | 0 |  |  | 0 | 0 | 0 | 0
NU | 0 | 0 |  |  | 0 | 0 | 0 | 0
EYCA | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
TOTAL | 294.5 | 1642007 | 152515.1 | 93400 | 1887922.1 | 105284.76 | 1993206.86 | 1993206.86 | 2000
HU | 65 | 346450 | 0 | 4200 | 350650 | 24545.5 | 375195.5 | 375195.5
EUF | 39 | 218439 | 0 | 12900 | 231339 | 0 | 231339 | 231339
GEANT | 32.5 | 276250 | 18000 | 6900 | 301150 | 19820.5 | 320970.5 | 320970.5
SRCE | 14 | 39200 | 0 | 4700 | 43900 | 3073 | 46973 | 46973
UB | 24.5 | 122500 | 0 | 4700 | 127200 | 8904 | 136104 | 136104
AUTh | 26 | 65000 | 3000 | 4700 | 72700 | 4879 | 77579 | 77579
CNOUS | 8.5 | 58786 | 10000 | 4200 | 72986 | 4409.02 | 77395.02 | 77395.02
STW | 11.5 | 76912 | 61515.1 | 4200 | 142627.1 | 5677.84 | 148304.94 | 148304.94
SRC | 21 | 160000 | 50000 | 4200 | 214200 | 11494 | 225694 | 225694
ECSTA | 10 | 60000 | 0 | 24900 | 84900 | 5943 | 90843 | 90843
ELTE | 14 | 56000 | 0 | 4700 | 60700 | 4249 | 64949 | 64949
ENDISU | 2.5 | 25000 | 10000 | 4200 | 39200 | 2044 | 41244 | 41244
NU | 20 | 100000 | 0 | 4700 | 104700 | 7329 | 112029 | 112029
EYCA | 6 | 37470 | 0 | 4200 | 41670 | 2916.9 | 44586.9 | 44586.9
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Budget per partner
Beneficiary name | Applicant budget(s) | State budget(s) | Regional/local budget(s) | Other sources | Requested CEF financing | Total
HU | 0 | 0 | 0 | 0 | 375195.5 | 375195.5
EUF | 0 | 0 | 0 | 0 | 231339 | 231339
GEANT | 0 | 0 | 0 | 0 | 320970.5 | 320970.5
SRCE | 0 | 0 | 0 | 0 | 46973 | 46973
UB | 0 | 0 | 0 | 0 | 136104 | 136104
AUTh | 0 | 0 | 0 | 0 | 77579 | 77579
CNOUS | 0 | 0 | 0 | 0 | 77395.02 | 77395.02
STW | 0 | 0 | 0 | 0 | 148304.94 | 148304.94
SRC | 0 | 0 | 0 | 0 | 225694 | 225694
ECSTA | 0 | 0 | 0 | 0 | 90843 | 90843
ELTE | 0 | 0 | 0 | 0 | 64949 | 64949
ENDISU | 0 | 0 | 0 | 0 | 41244 | 41244
NU | 0 | 0 | 0 | 0 | 112029 | 112029
EYCA | 0 | 0 | 0 | 0 | 44586.9 | 44586.9
0 |  |  |  |  | 0 | 0
0 |  |  |  |  | 0 | 0
0 |  |  |  |  | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 1993206.86 | 1993206.86

## xARCHIVE_2
|  |  | EUF | CNOUS | Geant | SRC | UGhent | ESN | UP | UW | AUTh | HU | UNIT | UMA | ENDISU | DSW | J1 | TOTAL
Activity 1 - eIDAS enabled authentication/eID infrastructure | Geant |  | 0 | 6 | 15 | 12 | 0 | 0 | 0 | 1 | 1 | 20 | 5 | 2 | 0 | 0 | 6 | 68
Activity Coordination |  |  |  |  | 6
Task 1 - Maintaining the European Student Card Router (ESC-R) + enabling national/local federated access | CNOUS | Jaume I |  | 6 | [12 empty] | 1
Task 2 - Maintaining the European authentication proxy for the eIDAS enabled eID | SRC |  |  |  |  | 12
Task 3 - Developing account linking feature for authentication of users | Geant | Jaume I |  |  | 3 | [11 empty] | 1
Task 4 - Developing guidelines to deploy national authentication proxies for the eIDAS enabled eID | Geant | Jaume I |  |  | 3 | [11 empty] | 1
Task 5 - Enabling student-centred data transfer (through the extension of the mandatory attributes provided by HEIs (ESI, etc.. )) | Geant |  |  |  | 3
Task 6 - Delivering European Student Card eCard open module + report | Humboldt | Malaga | [9 empty] | 20 |  | 2
Task 7 - Usability report of other eIDAS building blocks (eSignature, eDelivery, eArchive) | Jaume I | WAW/UNIT/AUTh | [7 empty] | 1 | 1 |  | 1 |  |  |  | 3
Task 8 - Performing ongoing security and privacy audits | UNIT | [11 empty] | 4
Activity 2 - Interoperability Infrastructure | Warsaw |  | 0 | 2 | 5 | 1 | 0 | 0 | 1 | 23 | 13 | 1 | 6 | 1 | 0 | 0 | 0 | 53
Activity Coordination | [9 empty] | 6
Task 1 - Updating requirements analysis | AUTh | Porto/WAW/ENDISU/CNOUS |  | 1 | [6 empty] | 3
Task 2 - Updating data model (notably ESI) | Warsaw | [8 empty] | 3
Task 3 - Updating data standard (ELMO) | UNIT | /Porto/Warsaw/CNOUS/HU |  | 1 |  |  |  |  | 1 | 1 |  | 1 | 2
Task 4 - Ensuring development and maintenance | AUTh
Task 4.1 - Enabling requirements for student mobility services (cycle 1) | AUTh | [9 empty] | 3
Task 4.2 - Enabling requirements for extended student services (cycle 2) | AUTh | [9 empty] | 3
Task 4.3 - Enabling interoperability with EC e-services (EU Login, MT+) | AUTh | [9 empty] | 3
Task 4.4 - Ensuring conflict resolution for multiple entrance points (Sentry server) | Warsaw | [8 empty] | 3
Task 4.5 - Implementing automated network access testing | Warsaw | [8 empty] | 3
Task 5 - Maintaining registry | Warsaw | [8 empty] | 3
Task 5.1 - Registry industrialisation | Warsaw | Geant/AUTh |  |  | 1 |  |  |  |  | 3 | 1
Task 5.2 - Managing (multiple) identifier updates | Geant | Warsaw/SRC/Malaga |  |  | 4 | 1 |  |  |  | 1 |  |  |  | 1
Task 6 - Performing ongoing security and privacy audits | UNIT | [11 empty] | 4
Activity 3 - Web service platform | Porto |  | 1 | 3 | 0 | 0 | 0 | 1 | 18 | 0 | 3 | 0 | 5 | 0 | 1 | 2 | 0 | 34
Activity Coordination | [8 empty] | 6
Task 1 - Adapting requirements analysis and information architecture | Porto | EUF/DSW/CNOUS | 1 | 1 |  |  |  |  | 3 | [6 empty] | 1
Task 2 - Blueprinting new functional requirements | Porto | AUTh | [6 empty] | 3 |  | 1
Task 3 - Setting up, developing and testing of web service (front-end/back-end) | Porto
Task 3.1 - Further enabling requirements for student mobility services (cycle 1) | Porto | AUTh | [6 empty] | 3 |  | 1
Task 3.2 - Enabling requirements for extended student services (cycle 2) | CNOUS | Porto | [6 empty] | 3 |  | 1
Task 4 - Performing ongoing security and privacy audits | UNIT | [11 empty] | 4
Task 5 - Blueprinting of a European student service portal | CNOUS | UNIT/ENDISU/DSW/ESN |  | 2 |  |  |  | 1 |  |  |  |  | 1 |  | 1 | 1
Activity 4 - Implementation of helpdesk services | UGhent |  | 3 | 1 | 0 | 0 | 38 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 48
Activity Coordination | [6 empty] | 6
Task 1 - Setup of technical helpdesk interface/tools | AUTh | [9 empty] | 6
Task 2 - Update of the knowledge base | UGhent | EUF/CNOUS | 1 | 1 |  |  | 3
Task 3 - Helpdesk service - team training | UGhent | EUF | 1 |  |  |  | 3
Task 4 - Operation of the helpdesk support | UGhent | EUF | 1 |  |  |  | 24
Task 5 - User satisfaction assessment | UGhent | [5 empty] | 2
Activity 5 - Roll-out and governance | EUF |  | 19 | 2 | 0 | 0 | 5 | 2 | 3 | 1 | 2 | 1 | 0 | 0 | 3 | 0 | 0 | 38
Activity Coordination |  |  | 6
Task 1 - Branding and communication strategy/kit | EUF | ENDISU | 2 | [11 empty] | 1
Task 2 - Defining the training strategy + creation of material + organising trainings | EUF | ENDISU | 2 | [11 empty] | 1
Task 3 - Implementing the main information portal | EUF | AUTh | 2 | [7 empty] | 1
Task 4 - Ensuring the EDSSI governance | EUF
Task 4.1 - Business process owner forum (SSP, IRO) | UGhent | DSW/CNOUS/ENDISU/ESN |  |  |  |  | 2
Task 4.2 - Technical stakeholder forum (NRENS, implementers) | AUTh | WAW/UP/CNOUS |  |  |  |  | 2
Task 4.3 - Policy forum | CNOUS | ESN/EUF | 1 | 2
Task 5 - Organising dissemination activities & participation to external conferences | EUF | ENDISU/ESN | 3 |  |  |  |  | 1 | [6 empty] | 1
Task 6 - Maintaining the Open Source University Alliance | Porto | EUF | 1 | [5 empty] | 2
Task 7 - Documenting roll-out by paragon implementer | UGhent | AUTh/Porto/WAW/HU/UGhent/ESN | 2 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Activity 6 - Management | EUF |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
Activity Coordination |  |  | 6
Task 1 - Coordination | EUF |  | 6
Task 2 - Financial management (budget control, distribution of funds) | EUF |  | 6
Task 3 - Quality Assurance & Evaluation | ENDISU?
Task 4 - Meeting organisation | EUF |  | 6
Task 5 - Sustainability & Transfer | EUF |  | 3
Task 6 - Legal capacity (DPO) | EUF |  | 3
GRAND-TOTAL |  |  | 53 | 14 | 20 | 13 | 43 | 3 | 22 | 25 | 25 | 22 | 16 | 3 | 4 | 2 | 6 | 271
Travel and subsistance per partner | 600
Number of pax Steering Committee per partner | 2
Number of pax Technical meeting per main technical partner | 2
Number of pax Technical meeting per secondary technical partner | 1
Number of pax Consortium meeting per partner | 2
Other costs in euro |  |  | 24000 | 24000 | 24000 | 24000 | 13200 | 3600 | 24000 | 24000 | 24000 | 3600 | 9000 | 8400 | 3600 | 3600 | 3600
SC1
SC2 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC3 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC4 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC5 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC6 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC7 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC8 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
SC9 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 |  | 1200 | 1200 | 1200 |  |  | 600 |  |  |  | 10200
TM1 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM2 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM3 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM4 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM5 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM6 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM7 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM8 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
TM9 |  |  | 1200 | 1200 | 1200 | 1200 |  |  | 1200 | 1200 | 1200 |  | 600 |  |  |  |  | 9000
Consortium Meeting 1 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 18000
Consortium Meeting 2 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 18000
Consortium Meeting 3 |  |  | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 18000
[16 empty] | Total meetings |  | 216600