## Slide 1: European Digital Student Service Infrastructure – Level 2
A seamless mobility experience,
enhanced by connected student e-services
The sole responsibility of this publication lies with the project consortium. The European Union is not responsible for any use that may be made of the information contained therein.
CEF-TC-2020-3
Date: | 16 11 2022
Presenter(s): | Stefan Liström Swedish Research Council
EDSSI L2 review meeting

## Slide 2: Activity 2 overview
Titel | Lead | Description | Planned duration | Status
Task 2.1 | Géant | Updating requirements analysis for building blocks and e-services | M1 – M4 | Delayed until M15
Task 2.2 | SRC | Building an eSignature solution | M5 – M12 | Delayed until M17
Task 2.3 | UB | Creating a Proof of concept for eArchive services | M13 – M23 | Just started
Task 2.4 | AUTh | Usability report of eTranslate CEF building block | M13 – M16 | Just started
Task 2.5 | SW-KA | Student housing Web-Application | M5 – M12 | On hold
Task 2.6 | EUF | Connecting e-services to the interoperability infrastructure | M13 – M20 | Just started

## Slide 3: Task 2.1 Updating requirements analysis for building blocks and e-services
Planned duration: M1 – M4
Indicator: Delivery of requirement report in M4 (Dec 2021)
Status: Ongoing, delayed. Expected delivery in M15 (Nov 2022)
Update: Report is in final review stage and focus on e-signature and e-archiving. Work on this report started late due to dependency on report from EDSSI L1 that was delayed. Cross collaboration between EDSSI L1 and EDSSI L2 was done to ensure this delay would not affect project outcomes.

## Slide 4: Task 2.2 - Building an e-Signature solution
Planned duration: M5 – M12
Indicator: Delivery of eSignature service in M12 (Aug 2022)
Status: Ongoing, delayed. Expected delivery M17 (Jan 2023)
Update: e-signature service up and running. Current work is focusing on integration of Aristotle University of Thessaloniki Certificate Authority to enable qualified signatures and the Online Learning Agreement portal to do a proof of concept of allowing students to e-sign their Online Learning Agreements.

## Slide 5: Task 2.3 - Creating a Proof of concept for eArchive services
Planned duration: M13 – M23
Indicator: Proof-of-concept by M20 (Apr 2022) and recommendation report by M23 (Aug 2023)
Status: Ongoing, just started
Update: Task is in prototyping phase at the moment using the RODA[1] solution to test eArchiving of the Erasmus Online Learning Agreements.
[1] https://github.com/keeps/roda

## Slide 6: Task 2.4 - Usability report of eTranslate CEF building block
Planned duration: M13 – M16
Indicator: eTranslate usability report by M16 (Dec 2022)
Status: Ongoing, just started
Update: A draft of the report is already written based on tests done with the EC e-Translate webservice and API. Further test and finalization of report is expected to be done by the end of the year.

## Slide 7: Task 2.5 - Student housing Web-Application
Planned duration: M5 – M12
Indicator: Proof-of-concept by M12 (Aug 2022) and recommendation report by M23 (Aug 2023)
Status: On hold
Update: Task is waiting for decision on budget changes to allow Studierendenwerk Karlsruhe to use subcontractors to work on this task. Detailed concept for the development of this web-application is already finalized but actual development has not started.

## Slide 8: Task 2.6 - Connecting e-services to the interoperability infrastructure
Planned duration: M13 – M20
Indicator: Recommendation report by M20 (Apr 2022)
Status: Ongoing, just started
Update: Coordination efforts are under way to ensure interoperability between all relevant tasks in the project.

## Slide 9
Questions?